## Sheet1
Deliverable | Intial Due date | Estimated Due Date | Acutal Due Date | Reasoning
Establishing Gitlab | 2020-10-14 |  | 2020-10-15 | Unable to decide betweeen gitlab or github
Setting up Environments | 2020-10-27 |  | 2020-10-29 | Focusing on another course exam did not set up the environment until afterwards
Learn Tutorials | 2020-10-29 |  | 2020-11-20 | Poor time management on the developers overwhelmed with coursework and recent family emergecies. Documentation regarding meeting with instructor
Hosting | 2020-10-31 |  | 11-16-2020 ( SiteGround) | Originally was going to use AWS educate from Github Developer Pack but switched to Wordpress rather than Django.
Domain | 2020-10-31 |  | 2020-11-15 | Issues with finding a decent price for Domain name
Point the Registered Domain | 2020-11-01 |  | 2020-11-20 | Domain from Godaddy is not registering to
Choose Templates | 2020-11-01 | 2020-11-21 |  | Confusion with implementating the project and underestimating the learning curve of Django. 3 deaths in the family ( Maternal Aunt, Maternal Uncle and Maternal Cousin)
Establish Basic Front and Backend | 2020-11-08 | 2020-11-21 |  | Poor time management and difficulty with
Work on Final Deliverables | 2020-11-12 | 2020-11-21 |  | Struggling with tool change and not being able to
Focus on Front End and backend | 2020-11-13 | 2020-11-22 |  | Family Emergency and underestimating the issues of finding plugins
Implement Plug In to Accept Foreign Currency | 2020-11-17 | 2020-11-25 |  | The frontend and backend are not complete
System Test Procecure | 2020-11-17 |  | 2020-11-20 | Did not have project established in time can provide estimations and also still creating website
Implement Capability of Adding Videos and Stories | 2020-11-20 | 2020-11-26
Implement Authenication for users | 2020-11-21 | 2020-11-26
Finalize Project Launch | 2020-11-29